FACULTY OF ENGINEERING

DEGREE ENGINEERING

DEPARTMENT OF COMPUTER ENGINEERING

SOFTWARE ENGINEERING (BE103505)

Unit-3 –Managing Software Project

Software Metrics

Measure:
A measure is a simple numerical value that shows the size, amount, or quantity of something in software, such as lines of code or number of errors.

Metrics:
Metrics are a combination of different measures used to understand the quality or performance of software. For example, average number of defects per hour.

Indicators:
Indicators are a group of metrics that help in understanding the overall condition of the software process, project, or product.

Direct Metrics:
Direct metrics are values that can be measured directly, such as number of lines of code, execution time, or number of defects.

Indirect Metrics:
Indirect metrics are qualities that cannot be measured directly, such as reliability, usability, or functionality.

Faults:
Faults are problems in software. Errors are faults found during development by developers, and defects are faults found by customers after release.

### Metric Classification

Software metrics are classified into three types: Process, Product, and Project metrics.

Process Metrics:
Process metrics are collected from many projects over time to improve the software development process. They focus on improving quality and making the process more efficient and repeatable. They are used for long-term improvement.

Error Categorization and Analysis:
In this method, errors are grouped based on their type or origin. The cost of fixing each error is recorded, and the total number of errors in each category is analyzed. This helps identify major problem areas and improve the process.

Project Metrics:
Project metrics are used by project managers to track progress, risks, and performance during development. They help in estimating time and cost, monitoring quality, and avoiding delays. Past project data is used to improve planning for new projects.

Product Metrics:
Product metrics focus on the quality of the final software product. They include measures like complexity of design, code structure, algorithm complexity, and data flow. These metrics help evaluate how good and efficient the software is.

Software Measurement

Direct Measures (Internal Attributes):
Direct measures are values that can be measured directly in software development, such as cost, effort, lines of code (LOC), speed, and memory usage.

Indirect Measures (External Attributes):
Indirect measures are qualities that cannot be measured directly but describe software performance, such as functionality, quality, complexity, efficiency, reliability, and maintainability.

### Size-Oriented Metrics

Size-oriented metrics are based on the size of the software, usually measured in KLOC (thousand lines of code). These metrics help compare productivity and quality.

Examples include:

- Errors per KLOC

- Defects per KLOC

- Cost per KLOC

- Pages of documentation per KLOC

- Errors per person-month

- KLOC per person-month

- Cost per page of documentation

### Function-Oriented Metrics

Function-oriented metrics measure software based on the functionality delivered to the user. The most common metric is the Function Point (FP). It is calculated based on the system’s features and complexity, not lines of code.

### Object-Oriented Metrics

Object-oriented metrics can use traditional measures like LOC or FP, but they are not very accurate for object-oriented systems. These metrics do not give detailed information needed for estimating effort and scheduling in iterative development.

### Use-Case–Oriented Metrics

Use-case metrics are based on use cases, which describe system functions from the user’s perspective. They are useful for early estimation before development starts. However, use cases can vary in size and detail, so it is difficult to standardize them for accurate measurement.

Software Project Estimation

Software project estimation is the process of predicting the cost, effort, and time required to complete a software project. It is a type of problem-solving activity, but it is complex, so it is broken into smaller parts to make it easier to estimate. For accurate estimation, experience, past project data (metrics), and careful judgment are needed.

### Software Sizing Techniques:

Fuzzy Logic Sizing:
This method uses approximate thinking instead of exact values. The project is first placed in a general category (small, medium, large), and then the size is refined within that range.

Function Point Sizing:
Estimates are made based on the system’s inputs, outputs, files, and user interactions rather than lines of code.

Standard Component Sizing:
The software is estimated based on reusable standard components used in similar types of applications.

Change Sizing:
Used when existing software is modified. It estimates how much work is needed for adding, changing, reusing, or deleting code.

### Problem-Based Estimation:

- First, define the overall scope of the project.

- Break the system into smaller functions.

- Estimate each function separately using LOC or Function Points.

- Use past productivity data (like LOC per person-month or FP per person-month) to estimate effort and cost.

- Combine all function estimates to get the total project estimate.

COCOMO Model (Empirical Process Model)

The COCOMO model is used to estimate the effort, cost, and time required to develop a software project. It uses the size of the software (like KLOC – Thousand Lines of Code) as input. It can also use Function Points or Object Points for estimation.

Application Composition Model:
Used in early stages of development. It is helpful for:

- Creating prototypes

- Checking system and software interaction

- Evaluating performance

- Checking technology feasibility

Early Design Model:
Used after requirements are clear and basic design is ready.

Post-Architecture Model:
Used during actual development and coding phase when system architecture is fully defined.

### Types of Software Projects:

Organic:
Simple projects with small teams and experienced developers. The system is well understood.

Semi-detached:
Medium complexity projects with mixed experience teams (some experienced, some new).

Embedded:
Complex projects that are tightly connected with hardware or strict rules and regulations.

### Basic COCOMO Formulas:

Effort = a × (KLOC)^b (Person-Months)
Time = c × (Effort)^d (Months)

### Effort Calculation:

- Organic: Effort = 2.4 × (KLOC)^1.05

- Semi-detached: Effort = 3.0 × (KLOC)^1.12

- Embedded: Effort = 3.6 × (KLOC)^1.20

### Time Calculation:

- Organic: Time = 2.5 × (Effort)^0.38

- Semi-detached: Time = 2.5 × (Effort)^0.35

- Embedded: Time = 2.5 × (Effort)^0.32

### Example (Simple):

For an organic project with 32 KLOC:

- Effort ≈ 91 person-months

- Development Time ≈ 14 months

- Cost = 14 × 15,000 = ₹2,10,000

Software Project Planning

The main objective of software project planning is to help the project manager estimate resources, cost, and time required to complete a software project. It also considers best-case and worst-case situations to understand possible outcomes. Since projects may change over time, the plan is continuously updated and improved during development.

### Task Set for Project Planning:

1. Establish Project Scope:
Define what the project will do and what is included or excluded.

2. Determine Feasibility:
Check whether the project is practical, possible, and worth doing.

3. Analyze Risks:
Identify possible problems that may affect the project.

4. Define Required Resources:

- Identify required team members and skills

- Identify reusable software components

- Identify tools, hardware, and other resources

5. Estimate Cost and Effort:

- Break the project into smaller parts

- Create multiple estimates using methods like size, function points, or use cases

- Compare and finalize the estimates

6. Develop Project Schedule:

- Divide work into proper tasks

- Arrange tasks in order

- Create a timeline for the project

- Track progress during development

Project Scheduling

Software project scheduling is the process of dividing the total estimated effort of a project into smaller software tasks and assigning them over a specific time period. It helps in planning when each task will be done. The schedule is not fixed and may change as the project progresses. In the early stage, a simple or overall schedule is created that includes major activities and functions.

### Scheduling Principles:

- The project is divided into small and manageable tasks and activities..

- Each task is given a proper start and end time based on its dependencies.

- The manager ensures enough team members are available to complete tasks on time.

- Each task is assigned to a specific team member.

- Every task must produce a clear output or deliverable.

- A milestone is reached when a task or set of tasks is completed and passes quality checks.

### Scheduling Techniques:

Software scheduling is similar to other engineering scheduling tasks, so standard methods can be used.

PERT (Program Evaluation and Review Technique):
Used to estimate project time using statistical methods and handle uncertainty in task durations.

CPM (Critical Path Method):
Identifies the longest sequence of tasks (critical path) that determines the total project duration.

Both PERT and CPM help to:

- Find the critical path of the project

- Estimate task completion times

- Calculate time ranges (best and worst case) for tasks

Risk Management

A risk is a possible problem that may or may not happen during a software project. It creates uncertainty in the project and can affect time, cost, or quality.

A risk is related to future events, and it involves uncertainty in decisions and actions. If a risk happens, it can lead to loss or damage such as delays or extra cost.

### Categories of Risk:

- Project Risks:
These risks affect the project plan. They can cause delays and increase project cost.

- Technical Risks:
These risks affect the software quality or development process. They may make implementation difficult or even impossible.

- Business Risks:
These risks affect whether the project is useful or worth doing. They can lead to project failure.

### Types of Risks:

- Known Risks:
These are risks that can be identified by analyzing the project plan and environment, such as unrealistic deadlines.

- Predictable Risks:
These risks are identified based on past project experience, such as team member turnover.

- Unpredictable Risks:
These risks are unexpected and very difficult to identify before they occur.

Risk Identification

One way to identify risks in a software project is by using a risk item checklist. This checklist helps the team find possible known and predictable risks by checking different areas of the project.

- Product Size:

Risks related to how big the software is. Larger systems may have more problems and take more time.

- Stakeholder Characteristics:

Risks related to users and clients. Problems may happen if communication between developers and stakeholders is weak.

- Process Definition:

Risks that occur if the development process is not clear or not properly followed by the team.

- Development Environment:

Risks related to tools, software, and hardware used in development. Poor tools can slow down the project.

- Technology to be Built:

Risks related to using new or complex technology. New technology may be difficult to understand and implement.

- Staff Size and Experience:

Risks related to the skills and experience of the development team. Less experienced teams may face more problems.

### Risk Estimation / Risk Projection

Risk estimation is the process of measuring and understanding risks in a software project. It helps to know how likely a risk is and how much damage it can cause.

### Risk Projection Steps:

- Set a scale (for example 1 = low risk, 10 = high risk) to measure risk likelihood.

- Describe what will happen if the risk occurs.

- Estimate the impact of the risk on the project cost, time, and quality.

- Note how accurate the risk prediction is to avoid misunderstandings later.

- Risk Mitigation, Monitoring, and Management (RMMM):

- Risk Mitigation:
It means planning in advance to prevent risks or reduce their impact before they happen.

- Risk Monitoring:
It means continuously checking whether risks are increasing or decreasing and observing team conditions and project progress.

- Risk Management:
It means taking action when a risk actually occurs, including backup plans and adjusting project work to reduce damage.

- Goal of RMMM:

- Identify all possible risks in the project.

- Estimate how likely each risk is to happen.

- Prepare plans to avoid or reduce risks.

- Track risks during the project.

- Create backup plans if risks occur.

### Risk Mitigation (Before the Risk Happens)

- Identify possible risks (e.g., team members may leave).

- Find the reasons for these risks.

- Fix problems that can be controlled.

- Prepare backup plans for risks that cannot be avoided.

- Share knowledge among team members.

- Keep proper documentation.

- Use peer reviews and assign backup people for important tasks.

### Risk Monitoring (During the Project)

- Continuously watch for warning signs of risks.

- Monitor team morale, workload, salary concerns, and job opportunities.

- Check if the mitigation plans are working.

- Ensure documentation is updated and easy to understand.

- Take early action if warning signs appear.

### Risk Management (After the Risk Happens)

- Activate the backup plan.

- Reassign work to available team members.

- Collect knowledge from the leaving employee.

- Train replacement team members using the documentation.

- Continue the project with minimum delay and keep it on track.